## Acticity
No | Activity | Detail | Duration
|  |  | MIN | MAX
1 | Design Matrix Competency | Pengumpulan data melalui pengamatan, diskusi dan analisis kebutuhan development competency akan dapat disusun secara sistematis bagaiman struktur jenjang karir dan tahapan pengembangan competency. Struktur ini tertuang dalam matrix competency. Dibuat buku Individual Development Program (IDP). | 1 Bulan | 3 Bulan
2 | Conduct TOT for Leaders | Conduct Training of Trainer sesi Teknik Melaksanakan Assessment yang akan membekali para leader (atasan) agar dapat melaksanakan assessment. | 1 hari | 3 hari
3 | Conduct Training Need Analysis | Melaksanakan assessment untuk mengetahui sejauh mana capaian competency masing-masing individu. | 2 Minggu | 1 Bulan
4 | Design Training Program | Melengkapi fasilitas, peralatan dan perlengkapan training. | 3 Bulan | 6 Bulan
Membuat modul atau materi training dan alat praktek (Training Aid).
Membuat aplikasi Learning Management System (LMS).
5 | Conduct Training | Deliver Training Basic Level Batch 1. | 1 Bulan | 2 Bulan
|  | Deliver Training Basic Level Batch 2. | 1 Bulan | 2 Bulan
6 | Conduct Monitoring On-the Job Training (OJT) | Memonitor jalannya program training dari aspek pengembangan skill melalui program On the Job Training. | 3 Bulan | 1 Tahun
7 | Conduct Assessment | Melaksanakan assessment untuk individu yang telah memenuhi persyaratan. | 1 Bulan | 2 Bulan

## Time Line-MIN
Duration MIN | Month
Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Design Matrix Competency
TOT for Leaders
Conduct Training Need Analysis
Design Training Program
Conduct Training
Conduct Monitoring OJT
Conduct Assessment

## Timeline-MAX
Duration MAX | Month
Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Design Matrix Competency
TOT for Leaders
Conduct Training Need Analysis
Design Training Program
Conduct Training
Conduct Monitoring OJT
Conduct Assessment

## Estimated Budget
DESCRIPTION | TYPE | QTY | UNIT | COST PER UNIT |  | TOTAL COST |  | NOTES
|  |  |  | MIN | MAX | MIN | MAX
Training Facility
Ruang Kelas | CAPEX | 1 | UNIT | 0 | 100000000 | 0 | 100000000 | Ruang Kelas dan Ruang lainnya dapat memakai ruang yang sudah ada
Ruang Praktek | CAPEX | 1 | UNIT | 0 | 300000000 | 0 | 300000000
Ruang Library | CAPEX | 1 | UNIT | 0 | 75000000 | 0 | 75000000
Ruang Toiletry | CAPEX | 1 | UNIT | 0 | 50000000 | 0 | 50000000
TOTAL | [5 empty] | 0 | 525000000
Perlengkapan
Meja dan Kursi Siswa | CAPEX | 20 | SET | 300000 | 700000 | 6000000 | 14000000
Meja dan Kursi Trainer | CAPEX | 2 | SET | 300000 | 700000 | 600000 | 1400000
AC (Pendingin Udara) | CAPEX | 2 | SET | 2000000 | 5000000 | 4000000 | 10000000
White Screen | CAPEX | 1 | PCS | 500000 | 3000000 | 500000 | 3000000
White Board | CAPEX | 1 | PCS | 500000 | 3500000 | 500000 | 3500000
Audio Sound System | CAPEX | 1 | SET | 500000 | 1500000 | 500000 | 1500000
LCD Projector | CAPEX | 1 | SET | 1000000 | 5000000 | 1000000 | 5000000
Lemari Arsip | CAPEX | 2 | SET | 1000000 | 2000000 | 2000000 | 4000000
Rak Buku | CAPEX | 4 | SET | 500000 | 1000000 | 2000000 | 4000000
Laptop/PC | CAPEX | 2 | PCS | 3000000 | 7000000 | 6000000 | 14000000
Perlengkapan Lainnya | CAPEX | 1 | PACK | 1000000 | 30000000 | 1000000 | 30000000
TOTAL | [5 empty] | 24100000 | 90400000
Training Material
Pembuatan Modul Training | CAPEX | 15 | PACK | 3000000 | 15000000 | 45000000 | 225000000
Pembuatan Aplikasi LMS | CAPEX | 1 | PACK | 0 | 150000000 | 0 | 150000000 | Design sendiri
[6 empty] | 45000000 | 375000000
Peralatan (Training Aids)
Hand Tools (Tool Box) | CAPEX | 3 | SET | 5000000 | 15000000 | 15000000 | 45000000 | Dapat meminjam dari Dept Service/Plant.
Special Tools | CAPEX | 1 | SET | 10000000 | 50000000 | 10000000 | 50000000
Power Tools | CAPEX | 1 | SET | 10000000 | 100000000 | 10000000 | 100000000
TOTAL | [5 empty] | 35000000 | 195000000
Training Delivery
Cetak Buku Panduan | OPEX | 20 | PACK | 100000 | 300000 | 2000000 | 6000000 | Asumsi 1 Batch training dengan peserta 2O siswa dan durasi training 41 Hari.
Cetak Lembar Pre Test dan Post Test | OPEX | 20 | PACK | 10000 | 20000 | 200000 | 400000
Alat Tulis dan Lain-lain | OPEX | 20 | PACK | 10000 | 50000 | 200000 | 1000000
Lunch | OPEX | 820 | PACK | 10000 | 25000 | 8200000 | 20500000
Coffee & Snack | OPEX | 820 | PACK | 3000 | 5000 | 2460000 | 4100000
Lain-lain | OPEX | 1 | PACK | 1000000 | 5000000 | 1000000 | 5000000
TOTAL | [5 empty] | 14060000 | 37000000
GRAND TOTAL | [5 empty] | 118160000 | 1222400000